### Creative City+ SIPF bid support – project inception notes

I’m following up the call with an annotated list of the elements proposed to Martyn.

My initial review of the data and the bid documentation suggested that the following tasks need to be carried out:

- Project inception meeting (via Zoom) with project partners

- Review EOI submission docs and assessors’ feedback – highlight areas of development needed in full bid documentation

- Strength in Places Fund context – differences between it and AHRC CIC, ISCF, etc

- Statistical base / supply chain analysis – scale and key employers:

  - Creative Industries (CI) within GM city region

  - Retail (physical) within GM city region

  - eCommerce within GM city region

- Value chains within creative and retail:

  - Creative content

  - Creative experience

  - Creative originals

  - Creative services

- Assets and opportunities (legacy into opportunities/horizon scanning)

  - In city region

  - In national and international markets

- Business and stakeholder engagement

  - Workshop with PI and CIs to identify key businesses/supply chain primes

  - Shortlist and agree approach to key commercial partners and stakeholders to the bid

  - Stakeholder engagement (up to six meetings of up to one hour’s duration)

- Seizing the opportunity

  - Options assessment

  - Review approach and methodology (Labs, etc)

  - Clearly differentiated value proposition / Case for change (logic model +) - based on HM Treasury ‘five case’ model

- Drafting bid response

- Appendices

The Gantt chart below suggests how these might be broken down into five work packages, and gives estimated timings for five key deliverables:

- Project initiation document

- Workshop presentation for PI and CIs to:

  - Present synthesis of findings of WP1 and WP2

  - Shortlist and prioritise key industry interlocutors and collaborators

  - Present initial draft framework theory of change and framework for options assessment

- Draft theory of change, presented in advance of preparation of text for bid

- Contribution to drafting bid response

- Delivery of technical appendices.